|  | - http://jurnal.unmer.ac.id/index.php/jtmt T R A N S M I S I ISSN (print): 9-772580-228020 - ISSN (online): 2580-2283 |  |
| --- | --- | --- |

The Lean Project Approach to Anticipate Delays in the Construction of 3.5 GT Fishing Boats (Case Study at PT. X)

Asfarina Hidayah 1

aUniversitas 17 Agustus 1945 Banyuwangi, Jl. Adi Sucipto No.26, Banyuwangi, 68416, Indonesia

*asfarina@untag-banyuwangi.ac.id

| INFORMASI ARTIKEL | ABSTRACT |
| --- | --- |
| Diterima: Direvisi: Disetujui: Tersedia online: | Projects generally have a deadline for completion. So far, PT. X often experiences delays in project completion. The problem is that waste often occurs in the production process. As a result, the company can suffer losses if waste m is not minimized immediately. The purpose of this research is to identify waste that contributes to delays in the construction of 3.5 GT fishing vessels and to increase the Value Stream by using the Lean Project methodology to estimate delays. Utilizing the Lean Project methodology, this research identifies and maps waste in every manufacturing step. The recommended value stream creation is based on the total time spent on each component, which is calculated from 18.7 hours to prepare the mould, 26.5 hours to manufacture the hull, 28 hours to assemble, 112 hours to manufacture the steering system, and 88 hours to manufacture the finish. The initial value stream for one unit of the Sumbawa 3.5 GT fishing vessel is 273 hours, or 34 days, according to the estimated time for each stage of the production process. The planned lead time is 678 hours or 84 days less than the previous lead time. The difference from the anticipated value stream is 405 hours or 51 days. Keywords: Lean Project, Value stream, Lead time |
|  | A B S T R A K |
| DOI: xxx | Proyek pada umumnya memiliki batas waktu pengerjaan.Selama ini PT. X sering mengalami keterlambatan dalam penyelesaian proyek. Kendalanya adalah sering terjadi waste pada proses produksi. Akibatnya perusahaan dapat mengalami kerugian jika waste m tidak segera diminimalkan. Tujuan dari penelitian ini adalah untuk mengidentifikasi pemborosan yang berkontribusi terhadap keterlambatan pembangunan kapal ikan 3,5 GT dan untuk meningkatkan Value Stream dengan menggunakan metodologi Lean Project untuk memperkirakan keterlambatan. Memanfaatkan metodologi Lean Project, penelitian ini mengidentifikasi dan memetakan pemborosan di setiap langkah manufaktur. Penciptaan value stream yang disarankan didasarkan pada total waktu yang dihabiskan pada setiap komponen, yang dihitung dari 18,7 jam untuk menyiapkan cetakan, 26,5 jam untuk membuat lambung, 28 jam untuk merakit, 112 jam untuk membuat sistem kemudi, dan 88 jam untuk menyelesaikan. Value stream awal untuk satu unit kapal penangkap ikan Sumbawa 3,5 GT adalah 273 jam, atau 34 hari, sesuai dengan perkiraan waktu untuk setiap tahapan proses produksi. Lead time yang direncanakan yaitu 678 jam atau 84 hari lebih kecil dari lead time sebelumnya. Selisih dari aliran nilai yang diantisipasi 405 jam atau 51 hari. Keywords :Lean Project, Value stream, Lead time 2020 Unmer. All rights reserved |

- Introduction

Intense competition and rapid changes in the corporate environment are the result of a period of economic globalization coupled with rapid technological developments. A company called PT X builds passenger boats, tugboats and fishing boats out of fiberglass, wood and steel on demand with the help of subcontractors (workers on a contract basis).

Based on the work orders distributed after the contract is concluded between the customer and the business, ship production at PT. X. So far, manufacturing results have fulfilled both domestic and international ship orders. The project to be worked on may be considered an order that the business has received. Most projects have a completion date, meaning the work must be completed ahead of schedule or on time. Currently, PT. X frequently faces delays in completion as a result of missed deadlines. The problem is that time is often wasted while waiting for one of them to complete an earlier task that has not been completed, resulting in many people losing their jobs.

Due to the inefficiency of the variables involved in project implementation (people, methods, materials, machines, and the environment), which may result in delays in project completion, the word waste is sometimes referred to as an activity that does not add value [1]. According to [2], the following eight wastes will apply to the maintenance industry: 1) Errors More commonly referred to as "rework" in the maintenance industry and are caused by work that does not meet requirements. Skills of worker technicians, suitability of processes to job applications, and substandard material specifications are just a few of the possible causes of this problem. 2) Extra Manufacturing When it comes to maintenance, it is possible to waste time and money by performing unnecessary maintenance. After treatment, breakdown (baby failure) is also possible. 3. Waiting Because the time needed to complete an activity is too long, there is no added value. Workers who are waiting for equipment or materials that have not arrived are also included. 4. Don't Use. This might be described as substandard utilization of resources. This includes assigning employees to tasks that are outside their area of ​​competence, which prevent the effective use of their skills. 5) The process of getting workers from office to workplace is referred to as transportation in a project. Taking too long during the transportation process wastes time and fuel. 6) Inventory In this case, it is understood to mean having abundant stock or goods. Waste often results from inadequate inventory inspections. In order for more of the same type of material to accumulate. In addition, as inventory builds up, inventory conditioning work will be required. If you don't do this, the inventory will be destroyed. 7) Migration This often occurs during the project, especially labor that is not needed, such as traveling back and forth between the office and the field, keeping tools, and the field as a result of equipment or information being left behind. 8) Overprocessing This waste comes from the use of improper work techniques, which causes the anticipated results to not meet the required standards.

Lean project management (LPM), which has concepts that can be used for the execution of production processes, or a lean thinking approach is needed to address this challenge.

Lean is an enterprise concept, systemic strategy and method for identifying and eliminating waste or non-value added operations through continuous improvement. This idea aims to eliminate all forms of waste and provide a smooth flow of goods during the value flow process [3]. To avoid delays and cost overruns during project implementation, [4]claims that the Lean Project Management methodology combines a Critical Chain Project Management (CCPM) approach to scheduling with lean tools to detect waste and its resources.

The following is the guiding concept of Lean Project Management [9]:

1. Project System a. Identify waste through fishbone diagrams and if-then statements

B. Use a work breakdown structure to identify specific tasks (WBS),

2. Managing Others

A. Name the parties involved.

B. Manage stakeholders by defining the tasks of each stakeholder using the RICA matrix, which is used for projects with multiple partners (usually up to hundreds).

3. Embarkation In the chartering phase, the vision and objectives of the project are established, and the project leader is assigned responsibility for the project plan. The project manager can use the charter form to simplify the charter steps so that relevant stakeholders can obtain information from related projects.

4. Ideal Response In choosing a way to deal with the waste that may develop during project implementation, this approach is applied.

5. Controlling Variation Since uncertainty in a project is known as variation, implementers must control variation by estimating before the project is executed in terms of cost, time (schedule), and resources used.

a. Cost projections. The first step is to estimate the project cost based on the required materials and labor (before 10% VAT and reserve money). The cost estimation process involves breaking down the labor and material requirements for each type of work.

B. Estimated timeframe. The Critical Chain Project Management (CCPM) approach to scheduling planning seeks to prevent Parkinson's law and the impact of student syndrome. A fresh answer to this problem is a scheduling technique known as Critical Chain Project Management (CCPM). 3, No. 1 (2017) Journal of Industrial Engineering Journal of Research Results and Scientific Papers of Industrial Engineering 41 The Critical Path Management (CPM) approach has developed into CCPM. One of the drawbacks of the CPM scheduling method is that the free time allocated to each activity causes resources to waste time available (Parkin's law effect), even though work can be completed more quickly or even workers tend to take work seriously. at the end of the work deadline.

c. Resource estimation. The need for the number of workers is inversely proportional to how long it takes to complete a task. More personnel are needed for jobs that take less time (less time) to complete, and vice versa.

6. Risk management for the project

7. Project Plan The idea of ​​lean project management is incorporated into the Project Plan.

8. Performance

A. Develop an integrated costing or schedule system B. Track time performance C. Implement project control procedures

Value stream mapping, sometimes referred to as big picture mapping, is a technique used to describe an entire system and the value streams that compose it, according to.[5]. Big picture mapping is useful for providing a macro-level description of the entire process, for visualizing process flow and lead times, and for identifying waste. Big picture mapping is used to map the real conditions that exist in the company than the organization has anticipated. [6].Any activity that uses resources but does not add value to consumers can also be seen as an activity or waste that does not add value[2].  The Critical Path Method (CPM), a technique for organizing and managing projects, is the most popular of the five systems that implement network development ideas, according to.[7]Activities with the longest implementation time are on the critical path (Critical Path). Therefore, the path indicated by the bold arrow as the important path is the path that most influences the overall project completion time[8]. The advantages of understanding the critical route according to [8].are as follows: A. All project work is delayed when work on the crucial path is delayed. B. If ongoing work on vital lines can be expedited, then project completion can be carried out more quickly. C. Completion of the critical path on time, and potential trade-offs (exchanging time for efficient costs) and crash programs (completed in the best possible time, accelerated with increased costs) or shortened time by adding overtime costs are ways to control supervision or management. D. Jobs that do not follow the critical route often have extra time available to them. This allows managers and projects to allocate resources more effectively and efficiently by moving labor, tools and costs to work the paths that matter.

By reducing waiting waste to anticipate project delays at PT.X, this study aims to apply the Lean Project idea to a 3.5 GT FRP fishing boat construction project. The following objectives will be achieved as a result of this study: 1. Understand the waste that contributes to the delay in the construction of 3.5 GT fishing vessels 2. Use the Lean Project methodology to increase the Value Stream to anticipate delays in the construction of 3.5 GT fishing vessels.

- Research methods

the process of collecting primary and secondary data to be studied. The 3.5 GT fishing boat construction project at PT. X is the subject of this research. The stages of this research include the following:

- collect primary and secondary data. Primary information was collected through observation and interviews. The time for each action in the construction of a 3.5 GT FRP fishing boat is determined by taking primary data. Secondary data is in the form of information obtained from documents for making fishing boats measuring 3.5 GT.

- Calculates standard time for each task.

- Network planning preparation. Making Network Planning is done to provide a visual picture of the sequence of work processes and the interdependence between the two.

- Finding the Critical Path is step d. The total duration of the longest process is determined using the Critical Path. From the initial node to the final node, the critical path is identified.

- Determine the Waiting Waste for each Critical Path activity.

- Diagram Identification of Causes and Effects of Waiting Waste.

- Collect suggested Value Streams. Assembling a suggested value stream depends on the location of the workforce and the amount of time spent on each part. The research flowchart is depicted in Figure 2.1.

- Picture 2.1 : Research Flowchart

Source : Processing Results data

3. Results and Discussion

3.1 Sequence data for the construction of the FRP 3.5 GT fishing boat

Table 3.1 provides information on work orders, normal working hours, and labor used in the construction of the Sumbawa fishing vessels.

table 3.1 Job order data, andman hours standart  Construction of a 3.5 GT fishing boat

| No. Activity | Name of activity | Predecessor Activites | Man Hours Standart(Hours) |
| --- | --- | --- | --- |
| 1 | Mold Preparation | 0 | 56 |
| 2 | Making Hull | 1 | 56 |
| 3 | Making deck | 1 | 56 |
| 4 | Contruction | 1 | 112 |
| 5 | Making Superstructure | 1 | 56 |
| 6 | Making component | 1 | 56 |
| 7 | Assambly | 2,3,4,5,6 | 168 |
| 8 | Installation Mechanical | 7 | 112 |
| 9 | Installation Electrical | 7 | 56 |
| 10 | Propulsion Installation | 7 | 56 |
| 11 | Steering system installation | 7 | 112 |
| 12 | Prosess Finishing | 8,9,10,11 | 224 |

- Source : calculating results

3.2 Calculation of Standard Time for each Activity

Wignjosoebroto, Sritomo calculates the standard time for each action in his book "Time And Motion Studies".

Standard time = Man Hours Standart (Person Hours)

Number of human resource (Person)

The standard time for each activity can be seen in table 4.3 below.

Calculation example:

- Mold preparation

Standard time = Man Hours Standart (Person Hours)

Number of human resource (Person)

hours

The results of calculating the standard time for each activity in the process of making a 3.5 GT fishing boat carried out at

PT.X can be seen in table 3.1

Table 3.1 Standard Time Calculation Results

| No. activity | Activity | Man Hours Standart | Number of Normal HR (People) | Standard Time (Hours) |
| --- | --- | --- | --- | --- |
| 1 | Mold preparation | 56 | 3 | 18.7 |
|  | Hull |  |  |  |
| 2 | a.Proses waxing | 5 | 3 | 1.7 |
| 3 | b. Processgelcoating | 16 | 3 | 5.3 |
| 4 | c. Lamination | 19 | 4 | 4.8 |
| 5 | d. Release from print | 16 | 4 | 4 |
|  | constructionHull |  |  |  |
| 6 | a. Making reinforcement | 40 | 6 | 6.7 |
| 7 | b. Skate making | 16 | 4 | 4 |
|  | Deck |  |  |  |
| 8 | a.Proses waxing | 5 | 3 | 1.7 |
| 9 | b. Processgelcoating | 16 | 3 | 5.3 |
| 10 | c. Lamination | 19 | 4 | 4.8 |
| 11 | d. Release from print | 16 | 4 | 4 |
|  | Superstructure |  |  |  |
| 12 | a.Proses waxing | 5 | 3 | 1.7 |
| 13 | b. Processgelcoating | 16 | 3 | 5.3 |
| 14 | c. Lamination | 19 | 4 | 4.75 |
| 15 | d. Release from print | 16 | 4 | 4 |
|  | Component |  |  |  |
| 16 | -Making of gold poles | 8 | 1 | 8 |
| 17 | - Making Place blower | 8 | 1 | 8 |
| 18 | - Door Making | 16 | 4 | 4 |
| 19 | - Window Creation | 8 | 4 | 2 |
| 20 | - Tank Creation | 16 | 4 | 4 |
| 21 | Assembly | 168 | 6 | 28 |
|  | InstallationMechanical |  |  |  |
| 22 | a..Inserting the machine | 8 | 2 | 4 |
| 23 | b. Installationengine mounting | 22 | 3 | 7.3 |
| 24 | c. Installation of cooling pipes | 32 | 3 | 10.7 |
| 25 | d. Installationexhause | 28 | 3 | 9.3 |
| 26 | e. InstallationGear box | 22 | 3 | 7.3 |
|  | InstallationElectrical |  |  |  |
| 27 | a.Installationswitch engine | 28 | 1 | 28 |
| 28 | b.Installation of lighting | 28 | 1 | 28 |
|  | Installationsteering system |  |  |  |
| 32 | a. Making the steering wheel | 24 | 1 | 24 |
| 33 | b. Manufacture of steering shoes | 16 | 1 | 16 |
| 34 | c. Making steering bosses | 16 | 1 | 16 |
| 35 | d) Install steering gear | 8 | 1 | 8 |
| 36 | e. Installation of the steering wheel | 8 | 1 | 8 |
| 37 | f. Steering bost installation | 8 | 1 | 8 |
| 38 | g. Installation of hydraulic cradle | 8 | 1 | 8 |
| 39 | h. Installationhelm pump | 8 | 1 | 8 |
| 40 | i. Installation of machinery | 8 | 1 | 8 |
| 41 | j. Installation of hydraulic hoses | 8 | 1 | 8 |
|  | Finishing |  |  |  |
| 42 | a. Glass installation | 8 | 2 | 4 |
| 43 | b. Door installation | 8 | 2 | 4 |
| 44 | c. Finish installation | 32 | 2 | 16 |
| 45 | d. Caulking + painting | 176 | 2 | 88 |

- Source : The calculation results

  - Identify Critical Paths

After making the network planning, the critical path is determined. The longest process duration is calculated using the critical route. Activities whose LS-ES equals 0 are activities that are on the critical (zero) path. Values ​​for the earliest and latest start for all activities.

Table 3.2 Value early start and lastest finish all activities.

| Tack |  | Time | IS | LF | LF-EN |
| --- | --- | --- | --- | --- | --- |
|  | Activity | Raw (Hours) |  |  |  |
|  | Design | - | 0 | 0 | 0 |
|  | Mold preparation | 18.7 | 18,7 | 18,7 | 0 |
|  | Hull |  |  |  |  |
|  | a.Proses waxing | 1.7 | 20,4 | 20,4 | 0 |
|  | b. Processgelcoating | 5.3 | 25,7 | 25,7 | 0 |
|  | c. Lamination | 4.8 | 30,5 | 30,5 | 0 |
|  | d. Release from print | 4.0 | 35,5 | 34,5 | 0 |
|  | Hull Construction |  |  |  |  |
|  | a.Reinforcrment manufacture | 6.7 | 41,2 | 41,2 | 0 |
|  | b. Skate making | 4.0 | 45,2 | 45,2 | 0 |
|  | Deck |  |  |  |  |
|  | a.Waxing process | 1.7 | 20,4 | 31,1 | 10,7 |
|  | b.Gelcoating process | 5.3 | 25,7 | 36,4 | 10,7 |
|  | c.Laminate | 4.8 | 30,5 | 41,2 | 10,7 |
|  | d. Release from the mould | 4.0 | 34,5 | 45,2 | 10,7 |
|  | Super structure |  |  |  |  |
|  | a.Waxing Process | 1.7 | 20,37 | 31,12 | 10,75 |
|  | b.Gelcoating Process | 5.3 | 25,7 | 36,45 | 10,75 |
|  | c.Laminate | 4.75 | 30,45 | 41,2 | 10,75 |
|  | d. Release from the mould | 4 | 34,45 | 45,2 | 10,75 |
|  | Component |  |  |  |  |
|  | -Pole manufacture | 8 | 26,7 | 27,2 | 0,5 |
|  | - Manufacture of blowers | 8 | 34,7 | 35,2 | 0,5 |
|  | - Door manufacture | 4 | 38,7 | 39,2 | 0,5 |
|  | - Window making | 2.0 | 40,7 | 41,2 | 0,5 |
|  | -Tank Manufacture | 4.0 | 44,7 | 45,2 | 0,5 |
|  | Assembly | 28.0 | 73,2 | 73,2 | 0 |
|  | Mechanical Installation |  |  |  |  |
|  | a.Enter the machine | 4 | 73,2 | 150,6 | 77,4 |
|  | b.Engine mounting installation | 7.3 | 84,5 | 157,9 | 73,4 |
|  | c. Cooling pipe installation | 10.7 | 95,2 | 168,6 | 73,4 |
|  | d.Exhaust Installation | 9.3 | 104,5 | 177,9 | 73,4 |
|  | e.Gear box Installation | 7.3 | 111,8 | 185,2 | 73,4 |
|  | Electrical installation |  |  |  |  |
|  | a.Switch engine Installation | 28 | 101,2 | 157,2 | 56 |
|  | b.Lighting installation | 28 | 129,2 | 185,2 | 56 |
|  | Propulsion installation |  |  |  |  |
|  | a. stern tube Installation | 8 | 81,2 | 165,2 | 84 |
|  | b.As propeller Installation | 8 | 89,2 | 173,2 | 84 |
|  | c.Alignment as propeller | 12 | 101,2 | 185,2 | 84 |
|  | Steering system installation |  |  |  |  |
|  | a.Manufacture of rudders | 24 | 97,2 | 97,2 | 0 |
|  | b. Manufacture of steering shoes | 16 | 113,2 | 113,2 | 0 |
|  | Rudder |  |  |  |  |
|  | c.steering wheel manufacture | 16 | 129,2 | 129,2 | 0 |
|  | d.Steering shoe installation | 8 | 137,2 | 137,2 | 0 |
|  | e. Steering wheel installation | 8 | 145,2 | 145,2 | 0 |
|  | f. Steering bracket installation | 8 | 153,2 | 153,2 | 0 |
|  | g.hydraulic jack installation | 8 | 161,2 | 161,2 | 0 |
|  | h. pump helmet installation | 8 | 169,2 | 169,2 | 0 |
|  | i. installation of jantra | 8 | 177,2 | 177,2 | 0 |
|  | j.hydraulic hose installation | 8 | 185,2 | 185,2 | 0 |
|  | Finishing |  |  |  |  |
|  | a.Glass installation | 4 | 77,2 | 156 | 78,8 |
|  | b.Door installation | 4 | 81,2 | 160 | 78,8 |
|  | C.finil installation | 16 | 97,2 | 176 | 78,8 |
|  | d.Caulking + Painting | 88 | 273,2 | 273,2 | 0 |

Source :The calculation results

From Network planning, the most prominent critical path is the installation partsteering system and finishing. In the installation section steering system takes 112 hours consisting of 24 hours of rudder making, 16 hours of steering gear making, 16 hours of rudder mounting, 8 hours of rudder shoe installation, 8 hours of rudder mounting, 8 hours of steering mounting, 8 hours of installation of hydraulic rudders , installationhelm pump 8 hours, 8 hours of manual installation, and 8 hours of hydraulic hose installation. Meanwhile in process finishing takes 88 hours. For more details about the activities included in the critical path, can be seen in Table 3.3

Table 3.3 Critical Path

Sumber : Hasil Perhitungan

| No | Activity |  | Activity No |  |  | Man Hours Standart | Number of Normal HR (People) | Standard Time (Hours) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Mold preparation |  | 1 |  |  | 56 | 3 | 18.7 |
|  | Hull |  |  |  |  |  |  |  |
| 2 | a. Waxing Process |  | 2 |  |  | 5 | 3 | 1.7 |
| 3 | b. gelcoating process |  | 3 |  |  | 16 | 3 | 5.3 |
| 4 | c. Lamination |  | 4 |  |  | 19 | 4 | 4.8 |
| 5 | d. Release from print |  | 5 |  |  | 16 | 4 | 4 |
|  | Construction Hull |  |  |  |  |  |  |  |
| 6 | a. Making reinforcement |  | 6 |  |  | 40 | 6 | 6.7 |
| 7 | b. Skate making |  | 7 |  |  | 16 | 4 | 4 |
| 8 | Assembly |  | 21 |  |  | 168 | 3 | 28 |
|  | Installation steering system |  |  |  |  |  |  |  |
| 9 | a. Making the steering wheel |  | 32 |  |  | 24 | 1 | 24 |
| 10 | b. Manufacture of steering shoes |  | 33 |  |  | 16 | 1 | 16 |
| 11 | c. Making a steering wheel boss |  | 34 |  |  | 16 | 1 | 16 |
| 12 | d) Install steering gear |  | 35 |  |  | 8 | 1 | 8 |
| 13 | e. Installation of the steering wheel |  | 36 |  |  | 8 | 1 | 8 |
| 14 | f. Steering bost installation |  | 37 |  |  | 8 | 1 | 8 |
| 15 | g. Installation of hydraulic cradle |  | 38 |  |  | 8 | 1 | 8 |
| 16 | h. Installation helm pump |  | 39 |  |  | 8 | 1 | 8 |
| 17 | i. Installation of machinery |  | 40 |  |  | 8 | 1 | 8 |
| 18 | j. Installation of hydraulic hoses |  | 41 |  |  | 8 | 1 | 8 |
|  | Finishing |  |  |  |  |  |  |  |
| 19 | Caulking + painting |  | 45 |  |  | 176 | 2 | 88 |
| Source :The calculation results SUMBERS |  |  |  |  |  |  |  |  |

3.3. Determination of the Initial Value Stream in the Making of the Sumbawa 3.5 GT Fishing Boat

The initial conditions for the process of making the Sumbawa 3.5 GT Fishing Boat are described invalue stream the beginning of the construction of fishing boats.Value stream the beginning starts from the preparation of the mold planned by the PPC section, followed by manufacturehull by the production department, processAssembly, Steering System, and the last processFinishing. Based on filmingbig picture mapping, obtained information that the first process is mold preparation. This process takes 56 hours. After the mold preparation is complete, proceed with the manufacturehull. Makinghull coverswaxing, gelcoating, lamination, and proceed with removalhull from mould. Next is constructionhull, starting with making reinforcement followed by making skates in the hull making process which takes 112 hours. After the hull manufacturing process is complete, proceed withAssembly.

Processassembly starting with assemblyhull, deck, construction,superstructure and components. This process takes 168 hours. After processassembly complete, proceed with the installationsteering system. This process includes the manufacture of rudders, the manufacture of rudders, the manufacture of rudders, the installation of rudders, the installation of rudders, the installation of rudders, the installation of hydraulic rudders, the installation ofhelm pump, installation of jantra, and installation of hydraulic hoses.

On installationsteering system takes 112 hours. After this process is complete, proceed with the last process, namely processfinishing which includes caulking and painting. On processfinishing takes 224 hours. Based on the detailed time for each stage of the process,lead time The process of making the Sumbawa 3.5 GT fishing boat can be determined by adding up the time needed for all these processes. The process of making one unit of the Sumbawa 3.5 GT fishing boat onvalue stream initial is 678 hours or 84 days.

3.4 Identification of Waiting Waste in Each Activity on the Critical Path

From several activities that are on the critical path, it is obtained that the installationsteering system is an activity that has the largest total percentage of waiting, namely 39.47%. After identificationwaste waiting through interviews and filling out questionnaires to the five expert employees involved in critical path activities to find out the causeswaste wait throughCause Effect Diagram.

In identification analysiswaste waiting on the critical path is known thatwaste waiting for the previous work station occurs due to previous activities that have not been completed, uneven workload, equipment damage in previous activities.Waste waiting because there are no production process procedures because the PPC division has not yet created a production procedure system, and workers are confused in carrying out their duties.Waste wait because the number of experts is limited because there are no additional experts, not all workers master the work techniques, experts are doing other work.Waste waiting due to the limited number of machines caused by the machine being used for other project processes, the lack of budget for procuring new machines, and the imbalance between production capacity and existing projects.

Following are the steps for detecting and weighing waste during the construction of fishing vessels:

- State the grade or weight of each selected waste.

All skilled workers involved in the construction of fishing vessels, in this case workers in the Fabrication and Finishing section, fill in a score or weight for each disposal. In table 3.4 below, there are guidelines for entering scores or weights.

Source :[10]

- The rating or overall mass of each litter.

Then, each work station adds up the score or weight of each waste provided by skilled employees at each station. The following is the calculation of the combined weight of each waste during finishing activities:

- Wait		= 3 + 2 +2 +3 = 10

- Calculates the combined weight and average weight of all waste.

The weight of each waste at each work station is added up to get the overall weight. total weight and average value of waste classified as “waiting” :

Total weight	 = 5 + 3 + 5 + 3 +……..3 + 2 + 10

= 76

- Calculate the proportion of the total weight of each waste in each work station.

By dividing the weight of the waste at the work stations by the total weight at all work stations, the total weight of the waste can be obtained as a percentage.

Table 3.5 presents a summary of the proportion of the total weight of each waste at each work station.

Table 3.5 Rekapitulasion of the percentage of waiting waste

|  |  | Waste | Percentage |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Activity | Wait | Waste Wait |  |  |
|  | Mold preparation | 5 |  | 6.58% |  |
|  | Hull |  |  |  |  |
|  | a.Waxing Process | 3 |  | 3.95% |  |
|  | b. Gelcoating Process | 5 |  | 6.58% |  |
|  | c. Lamination | 3 |  | 3.95% |  |
|  | d. Release from print | 5 |  | 6.58% |  |
|  | Construction Hull |  |  |  |  |
|  | a. Making reinforcement | 3 |  | 3.95% |  |
|  | b. Skate making | 3 |  | 3.95% |  |
|  | Assambly | 9 |  | 11.84% |  |
|  | Installation steering system |  |  |  |  |
|  | a. Making the steering wheel | 3 |  | 3.95% |  |
|  | b. Manufacture of steering shoes | 4 |  | 5.26% |  |
|  | c. Making a steering wheel boss | 3 |  | 3.95% |  |
|  | d) Install steering gear | 2 |  | 2.63% |  |
|  | e. Installation of the steering wheel | 4 |  | 5.26% |  |
|  | f. Steering bost installation | 4 |  | 5.26% |  |
|  | g. Installation of hydraulic cradle | 3 |  | 3.95% |  |
|  | h. Installation helm pump | 2 |  | 2.63% |  |
|  | i. Installation of machinery | 3 |  | 3.95% |  |
|  | j. Installation of hydraulic hoses | 2 |  | 2.63% |  |
|  | Finishing |  |  |  |  |
|  | Caulking + painting | 10 |  | 13.16% |  |
| Total Weight |  | 76 |  | 100.00% |  |

Source : The calsulation results

3.4 Recommendations for Improvements to Waste Waiting

Cause of occurrence waste waiting to use Cause Effect Diagram shown in figure 3.1.

Picture 3.1 Cause effect diagram waste wait

Source: Results of Data Processing

Based on identification analysiswaste wait throughCause Effect Diagram in table 3.1 there are several improvements that must be made so that the project can run optimally.

1. Waste waiting for the previous workstation

- The process of the previous activity has not been completed. while waiting for the previous work to be completed, they can do work that can be done in parallel so that the workforce can still work.

- Unequal workload. There must be an even distribution of workload in each activity so that the next activity is not hampered. And can do the addition of human resources in accordance with production needs.

- There was damage to the equipment in the previous activity.Maintenance production equipment is carried out periodically to anticipate further equipment damage.

2. Waste waiting because there is no procedure for the production process

- The PPC division has not yet made a system of production procedures. the PPC section must make Production Operational Standards (SOP) and planningmaster schedule per project

- Workers are confused in carrying out their duties. The production department must create an organizational structure per project so that if workers are confused in carrying out their duties, they can ask the person in charge of each project.

3. Waste wait because the number of experts is limited

- Not all workers master the work technique. Should be donemanagement Training to expert staff according to their respective fields.

- There are no additional experts. Adding competent experts according to their fields.

- The workforce is doing other work.Job description  experts must be clear, so that experts have responsibility for the project being worked on.

4. Waste waiting because the number of machines is limited

- The machine is being used to process another project. madeschedule machine usage per project.

- Lack of budget for the procurement of new machines. Empowerment of production machines so they can be used again.

- Unbalance between production capacity and existing projects. Production machine facilities must be added as needed.

3.5 Preparation of the Proposed Value Stream

Creating a suggested value stream based on the overall time spent on each component—18.7 hours for moulding, 26.5 hours for hull, 28 hours for assembly, 112 hours for steering system, and 88 hours for finishing—was completed. Based on the detailed time for each stage of the process,lead time The process of making the Sumbawa 3.5 GT fishing boat can be determined by adding up the time needed for all these processes.

. 	The process of making one unit of fishing boat 3.5 GT onvalue stream proposal is 273.2 hours or 34 days.Lead time it's smaller in comparisonlead time before that was 678 hours or 84 days. Difference 404.8 hours or 51 days fromvalue stream proposal. To be clearvalue stream The proposal can be seen in Figure 3.2.

Picture 3.2 . Proposed value streams

Source : Calculation results

- Conclusion

The conclusions in this study are:

1. Based on identification analysiswaste wait throughCause Effect Diagram there are several improvements that must be made so that the project can run optimally.

- Waste waiting for the previous workstation

- Waste waiting because there is no procedure for the production process

- Waste wait because the number of experts is limited

- Waste waiting because the number of machines is limited

2. The recommended value stream creation is based on the total time spent on each component, which is calculated from 18.7 hours to prepare the mould, 26.5 hours to build the hull, 28 hours to assemble, 112 hours to manufacture the rudder system, and 88 hours to complete. The lead time for the construction of the Sumbawa 3.5 GT fishing boat can be calculated by adding up the time required for each of these procedures based on the time specifications for each stage of the process. The process of making one unit of the Sumbawa 3.5 GT fishing boat onvalue stream the beginning is 273.2 hours or 34 days.

Compared to the previous lead time of 678 hours or 84 days, the anticipated lead time is shorter. The difference from the anticipated value stream is 404.8 hours, or 51 days. Figure 4.2 for the original value stream and Figure 4.5 for the suggested value stream provide further information.

- Acknowledgments (Optional)

Thank you to PT.X for facilitating the process of completing this study.

Reference

[1]Gray, C. and Larson, E. 2006. The ManagerialProcess 3th Edition. McGraw-Hill Company,New York.

[2]George, Michael L., et al. 2005. The Lean Six Sigma Pocket Toolbook. New York : McGraw-Hill, 2005.

[3]Gasperz, Vincent. 2006. Continuous Cost Reduction Through Lean-Sigma Approach. Jakarta : Gramedia Pustaka Utama, 2006.

[4]Leach, L. P. 2005. Lean ProjectManagement:Eight Principles for Success.Artech House, Norwood.

[5]Womack, James P. dan Jones, Daniel T. 2003. Lean Thinking : Banish Waste and Create Wealth in Your Corporation Second Edition. New York : Free Press, 2003.

[6]Hines, Peter dan Rich, Nick. 1997. 1997, International Journal of Operations & Production Management, hal. 46-64.

[7]Levin, Richard I. dan Charles A Kirkpatrick. 1972. Perentjanaan dan Pengawasan Dengan PERT dan CPM. Jakarta : Bhratara.

[8] Badri, S. 1997. Dasar-dasar Network Planing. Jakarta : PT Rika Cipta.

[9]Untu, Silvia Hermina Stevania, Ariestides K. T. Dundu,dan Robert J. M. Mandagi. Penerapan Metode Lean Project Management dalam Perencanaan Proyek Konstruksi (Studi Kasus : Pembangunan Gedung Mantos Tahap III). Jurnal Sipil Statik Vol. 2 No. 6. September, 2014. http://www.download.portalgaruda.org. Diakses pada tanggal 27 November 2014.

[10] Hirano, Hiroyuki.1990. The Complete Guideto Just-In-Time Manufacturing, Portland Publishing, United States Of America.